SEO & AI SEARCH PROPOSAL

Gandum Uluwatu

Boutique Stay  ·  Restaurant  ·  Spa

Monthly SEO, Local SEO & AI Search Optimisation (GEO / AEO / LLM SEO), with a 90-Day Growth Plan

Website: gandumuluwatu.com

Prepared for: Gandum Uluwatu Management

Prepared by: [Your Name / Agency Name]

Date: 18 October 2026

Proposal valid until: 17 November 2026

# Contents

(If the contents list appears empty, right-click it in Word and choose “Update Field”.)

# 1. Executive Summary

Gandum Uluwatu runs three businesses from one website: the Boutique Stay, the Restaurant and the Spa, each with its own Google Business Profile. That gives you three ways to be found: in Google search, in Google Maps, and in the answers given by AI assistants such as ChatGPT, Gemini, Perplexity and Google AI Overviews.

This proposal sets out one SEO and AI-search programme covering all three businesses. Its goal is more direct room bookings, more restaurant guests and more spa appointments, not just higher rankings.

## What we will do

- Fix the foundation: tracking, technical health, schema markup, and a clean-up of the backlink profile.

- Win local search: fully optimise and actively manage all three Google Business Profiles to grow Maps visibility.

- Publish with a plan: 10 SEO blog articles per month, built around topic clusters that answer the questions travellers ask before they book.

- Build authority: 100 backlinks and mentions per month from a balanced mix of sources.

- Get cited by AI: structure the website and content so AI assistants can understand, trust and recommend Gandum Uluwatu.

- Stay transparent: every working sheet is shared with you live, nothing goes live without your approval, and you get a full report every month.

# 2. Where You Stand Today

Baseline from Semrush, Domain Overview for gandumuluwatu.com (Worldwide, desktop, 17 October 2026):

| Metric | Current value | What it means |
| --- | --- | --- |
| Authority Score | 9 / 100 | Low. Google sees limited trust in the domain. |
| Organic traffic (est.) | 6 visits / month | Almost no visitors come from Google search today. |
| Organic keywords | 96 (+13%) | Some rankings exist, but few are in positions that bring clicks. |
| Referring domains / backlinks | 1.3K / 1.4K | Many links but low authority. These links are likely low quality and need an audit. |
| Paid traffic | 0 | No paid search activity. |
| AI Visibility | 14 | Low presence in AI answers. |
| AI mentions | 2 (ChatGPT 1, Gemini 1) | AI assistants rarely mention the brand. |
| AI cited pages | 5 (AI Overviews 2, AI Mode 1, Gemini 2) | A small base to build on. |

Key insight The domain has more than 1,300 referring domains but an Authority Score of only 9. That usually means most of the existing links are low quality or spammy, so they add little value and can hold the site back. Month 1 therefore starts with a backlink audit and clean-up (disavowing toxic links where needed) before new links are built. New authority should go toward a clean profile.

Semrush figures are third-party estimates. We will confirm the real baseline from your Google Search Console, GA4 and Google Business Profile data in the first week.

# 3. Scope of Work

## 3.1 On-Page SEO

- Keyword research and mapping a target keyword to every key page (Stay, Rooms, Restaurant, Menu, Spa, Treatments, Contact)

- Meta titles and descriptions written for click-through

- Heading structure (H1–H3), content optimisation and FAQ sections

- Internal linking between the Stay, Restaurant, Spa and blog pages

- Image optimisation: compression, WebP, file names and alt text

- Clear calls to action that lead to booking, reservation and treatment enquiries

## 3.2 Technical SEO

- Full technical audit: crawlability, indexing, broken links, redirects, duplicate content and sitemaps

- Page speed and Core Web Vitals, mobile optimisation

- Schema markup: Hotel / LodgingBusiness, Restaurant (with menu), DaySpa, Organization, FAQ, Review and Breadcrumb

- Google Search Console and Bing Webmaster Tools set-up and monitoring

- Backlink audit and disavow file for toxic links

## 3.3 Content SEO

- 10 SEO-optimised blog articles per month (1,200–2,000 words each, written by people, edited for accuracy)

- Keyword research for blogs and for landing pages, kept as two separate plans (see sections 4 and 5)

- Content gap analysis against competing hotels, restaurants and spas in Uluwatu

- Landing page recommendations, e.g. “Honeymoon Stay”, “Couples Massage” and “Breakfast in Uluwatu”

## 3.4 Local SEO: 3 Google Business Profiles

- Complete optimisation of all three profiles: categories, services, menu, treatments, attributes, descriptions, photos and Q&A

- 10 Google Business Profile posts per month (offers, events, menu highlights, spa specials)

- Review-generation strategy and reply templates

- NAP (name, address, phone) consistency across all directories, plus Bing Places and Apple Business Connect

- Local citations on travel, food and wellness directories

## 3.5 Off-Page SEO: 100 Backlinks per Month

| Link type | Per month | Purpose |
| --- | --- | --- |
| Business listings & local citations | 30 | Local trust and consistent NAP for Maps rankings |
| Web 2.0 properties | 20 | Branded content hubs that link to key pages |
| Article submissions | 15 | Topic-relevant contextual links |
| High-authority platform publishing (Medium, LinkedIn, Substack, Quora, etc.) | 15 | Branded visibility on platforms that AI assistants often cite |
| Free guest posts (travel / food / wellness) | 10 | Relevant editorial links |
| PR submissions | 10 | Brand mentions and news-style coverage |
| Total | 100 |  |

All links point to relevant pages and use natural anchor text. Every link is logged in a shared sheet with its URL, type, target page and date.

## 3.6 AI Search Optimisation (AI SEO, LLM SEO, AEO, GEO)

- AI visibility baseline: track a fixed set of prompts (e.g. “best boutique hotel in Uluwatu”, “best spa in Uluwatu”) across ChatGPT, Gemini, Perplexity and Google AI Overviews

- Answer-first content: clear, quotable answers, FAQ blocks and comparison tables that AI assistants can lift

- Entity building: consistent brand facts across the website, Google, TripAdvisor, booking sites and directories, so AI models know who you are

- Getting listed on “best of Uluwatu” articles and listicles, which AI assistants often use as sources

- Bing optimisation, since ChatGPT search relies heavily on Bing’s index

- An llms.txt file and AI-crawler access checks

- Monthly AI visibility tracking: mentions, citations and share of voice compared with competitors

## 3.7 Competitor Research

- Identify the top competitors for each business (stay, restaurant, spa) in search, Maps and AI answers

- Compare their keywords, backlinks, content and Google Business Profiles to find quick wins and gaps

## 3.8 Tracking, Reporting & Transparency

- Set up all tracking tools: GA4 (with booking, reservation, WhatsApp and call-click events), Google Search Console, Bing Webmaster Tools, rank tracker and AI-visibility tracker

- Monthly report sheet: keyword rankings, website traffic, GA4 and GSC reports, Google Business Profile insights, backlinks built and AI visibility

- A live dashboard you can check at any time

- All working and reporting sheets are shared with you, and you have access to them throughout the project

- Nothing is published, on the website or anywhere else, until you have reviewed and approved it

# 4. Keyword Strategy: Website & Landing Pages

These are commercial, “ready to book” keywords. They are targeted by the core website pages and new landing pages, not by blog articles. Search volumes and difficulty will be confirmed in Month 1 keyword research.

## 4.1 Boutique Stay

| Target keyword | Target page | Intent |
| --- | --- | --- |
| boutique hotel Uluwatu | Home / Stay page | Book |
| where to stay in Uluwatu | Stay page | Compare & book |
| Uluwatu accommodation | Stay page | Book |
| boutique villa / guesthouse Uluwatu | Rooms page | Book |
| hotel near Uluwatu Temple / beaches | Location section | Book |
| Uluwatu honeymoon stay | New landing page | Book |
| hotel with pool Uluwatu | Rooms page | Book |
| Gandum Uluwatu (brand) | Home page | Brand |

## 4.2 Restaurant

| Target keyword | Target page | Intent |
| --- | --- | --- |
| restaurant Uluwatu | Restaurant page | Visit |
| best restaurants in Uluwatu | Restaurant page | Compare & visit |
| breakfast / brunch Uluwatu | New landing page | Visit |
| dinner in Uluwatu | Restaurant page | Visit |
| Indonesian / Balinese food Uluwatu | Menu page | Visit |
| healthy / vegan food Uluwatu | Menu page | Visit |
| romantic dinner Uluwatu | New landing page | Visit |
| restaurant near me (Uluwatu, via Google Maps) | Restaurant Google profile | Visit |

## 4.3 Spa

| Target keyword | Target page | Intent |
| --- | --- | --- |
| spa Uluwatu | Spa page | Book |
| massage Uluwatu | Spa page | Book |
| best spa in Uluwatu | Spa page | Compare & book |
| Balinese massage Uluwatu | Treatments page | Book |
| couples massage Uluwatu | New landing page | Book |
| spa packages Uluwatu / Bali | Treatments page | Book |
| body scrub / lulur Uluwatu | Treatments page | Book |
| post-surf massage Uluwatu | New landing page | Book |

# 5. Keyword Strategy: Blog Content Plan (Months 1–3)

Blog keywords are informational: questions travellers ask before choosing where to stay, eat or relax. They are kept separate from the website keywords on purpose, so blog posts never compete with the booking pages. Instead, every article links to the relevant booking page.

These topics are also the questions AI assistants are asked most, so each article uses an answer-first structure, FAQs and clear facts to improve the chance of being cited.

## Month 1: Uluwatu Travel Foundations

| # | Blog title | Primary keyword | Supports |
| --- | --- | --- | --- |
| 1 | Where to Stay in Uluwatu: Complete Area Guide (2026) | where to stay in Uluwatu | Stay |
| 2 | Best Things to Do in Uluwatu | things to do in Uluwatu | All |
| 3 | Uluwatu Temple & Kecak Fire Dance: Tickets, Times & Tips | Uluwatu Temple Kecak dance | Stay |
| 4 | Best Beaches in Uluwatu: Padang Padang, Bingin, Melasti & More | best beaches in Uluwatu | Stay |
| 5 | Where to Eat in Uluwatu: A Local Food Guide | where to eat in Uluwatu | Restaurant |
| 6 | Traditional Balinese Massage: What to Expect | Balinese massage | Spa |
| 7 | How to Get from Bali Airport to Uluwatu | Bali airport to Uluwatu | Stay |
| 8 | Best Time to Visit Uluwatu (Month-by-Month) | best time to visit Uluwatu | Stay |
| 9 | Couples Spa Day in Uluwatu: Ideas & Packages | couples spa Uluwatu | Spa |
| 10 | Uluwatu Surf Guide for Beginners | Uluwatu surf beginners | Stay / Spa |

## Month 2: Experiences & Comparisons

| # | Blog title | Primary keyword | Supports |
| --- | --- | --- | --- |
| 11 | Uluwatu Honeymoon Guide: Stay, Dine & Unwind | Uluwatu honeymoon | All |
| 12 | The Perfect 3-Day Uluwatu Itinerary | Uluwatu itinerary | All |
| 13 | Best Sunset Spots in Uluwatu | Uluwatu sunset | Stay / Restaurant |
| 14 | 10 Balinese Dishes You Must Try | Balinese food | Restaurant |
| 15 | Breakfast & Brunch in Uluwatu: A Guide | brunch Uluwatu | Restaurant |
| 16 | Balinese Lulur & Boreh Scrubs: Benefits Explained | Balinese lulur scrub | Spa |
| 17 | Post-Surf Recovery: Why a Massage Helps | massage after surfing | Spa |
| 18 | Uluwatu vs Canggu vs Seminyak: Where Should You Stay? | Uluwatu vs Canggu | Stay |
| 19 | Is Uluwatu Worth Visiting? Honest FAQ | is Uluwatu worth visiting | Stay |
| 20 | Workation in Uluwatu: A Guide for Digital Nomads | Uluwatu digital nomad | Stay |

## Month 3: Niche Audiences & Wellness

| # | Blog title | Primary keyword | Supports |
| --- | --- | --- | --- |
| 21 | Family-Friendly Uluwatu: Where to Stay & What to Do | Uluwatu with kids | Stay |
| 22 | Vegetarian & Vegan Food in Uluwatu | vegan Uluwatu | Restaurant |
| 23 | Romantic Dinner Ideas in Uluwatu | romantic dinner Uluwatu | Restaurant |
| 24 | First Time at a Bali Spa? Etiquette & FAQ | Bali spa etiquette | Spa |
| 25 | Balinese vs Thai vs Deep Tissue Massage: Which to Choose? | types of massage Bali | Spa |
| 26 | Uluwatu in Rainy Season: Is It Still Worth It? | Uluwatu rainy season | Stay |
| 27 | Best Day Trips from Uluwatu | day trips from Uluwatu | Stay |
| 28 | A Wellness Weekend in Uluwatu: Stay + Spa Guide | wellness retreat Uluwatu | Stay / Spa |
| 29 | Uluwatu Beach Clubs & Nightlife Guide | Uluwatu beach clubs | Stay |
| 30 | Uluwatu on a Budget vs Luxury: Costs Compared | Uluwatu travel cost | Stay |

Titles and keywords are the initial plan. They will be refined after the Month 1 keyword research and content gap analysis, and every article is sent to you for approval before it is published.

# 6. 90-Day Strategy & Roadmap

## Month 1: Foundation & Fix

- Onboarding, access collection and set-up of all tracking (GA4 events, GSC, Bing, rank tracker, AI-visibility tracker, dashboard)

- Full technical SEO audit and the first round of fixes

- Backlink audit and toxic-link disavow

- Competitor research for the stay, restaurant and spa

- Keyword research and mapping for the website and the blog

- Full optimisation of all 3 Google Business Profiles

- Schema markup for the Hotel, Restaurant and Spa

- On-page optimisation of core pages

- AI visibility baseline report

- 10 blogs, 100 backlinks, 10 Google Business Profile posts

## Month 2: Build & Expand

- Content gap analysis, then new landing page recommendations

- Internal linking structure across all pages and blogs

- AEO/GEO upgrades: FAQ blocks, answer-first rewrites of key pages, llms.txt

- Entity consistency across TripAdvisor, booking sites, Bing Places and Apple Business Connect

- Review-generation system for all 3 businesses

- 10 blogs, 100 backlinks, 10 Google Business Profile posts

## Month 3: Authority & AI Visibility

- Outreach for inclusion in “best of Uluwatu” articles and listicles

- PR and brand-mention push; reclaiming unlinked brand mentions

- Refresh and improve the best-performing pages and blogs

- Booking-conversion review (CTAs, WhatsApp and booking flow)

- Quarterly review and a strategy plan for months 4–6

- 10 blogs, 100 backlinks, 10 Google Business Profile posts

## 90-Day Targets

| KPI | Today | Target by Day 90 |
| --- | --- | --- |
| Organic keywords | 96 | 250+ |
| Authority Score | 9 | 15+ |
| AI mentions (tracked prompts) | 2 | 10+ |
| Google Business Profile completeness | Not yet audited | 100% on all 3 profiles |
| Published SEO blogs | — | 30 |
| New quality backlinks | — | 300 |
| Tracking & reporting | Not yet audited | Fully set up & live |

These are directional targets, not guarantees. SEO results depend on search-engine algorithms, competition and how quickly approvals and website changes happen. SEO compounds over time, and the strongest gains in traffic and bookings usually come from months 4 to 6 onwards.

# 7. Monthly Packages & Pricing

Three packages are available. All of them cover the Boutique Stay, Restaurant and Spa on one website, plus all three Google Business Profiles. Horizon is the recommended package and includes the full scope described in this proposal.

| Deliverable | Sunrise Foundation | Horizon Growth (Recommended) | Summit Market Leader |
| --- | --- | --- | --- |
| Monthly investment (USD) | $549 | $899 | $1,499 |
| SEO blog articles / month | 5 | 10 | 15 |
| Backlinks / month | 50 | 100 | 150 |
| Google Business Profile posts / month | 6 | 10 | 15 |
| Optimisation of all 3 Google Business Profiles | ✓ | ✓ | ✓ |
| Keyword research (blogs + landing pages) | ✓ | ✓ | ✓ |
| Competitor research | Top 3 overall | Top 5 per business | Top 5 per business + quarterly deep dive |
| Technical SEO audit & fixes | Audit + key fixes | ✓ | ✓ |
| On-page SEO & schema markup | ✓ | ✓ | ✓ |
| Backlink audit & disavow | ✓ | ✓ | ✓ |
| AI SEO / LLM SEO / AEO / GEO | Basic (schema + FAQ) | Full | Full + listicle outreach |
| Content gap analysis | — | ✓ | ✓ |
| AI visibility tracking | Quarterly | Monthly | Monthly + competitor share of voice |
| New landing pages / month | — | 1 | 2 |
| Review-generation system | — | ✓ | ✓ |
| Digital PR outreach (earned media) | — | — | ✓ |
| Booking-conversion optimisation | — | — | ✓ |
| Tracking set-up (GA4, GSC, Bing, rank tracker) | ✓ | ✓ | ✓ |
| Monthly ranking & traffic report sheet | ✓ | ✓ | ✓ |
| GA4 & GSC traffic reports | ✓ | ✓ | ✓ |
| Live shared working sheets & dashboard | ✓ | ✓ | ✓ |
| Client approval before anything is published | ✓ | ✓ | ✓ |
| Strategy call | Monthly email summary | Monthly call | Bi-weekly call |
| Support | Email | Email + WhatsApp | Priority, same day |

## Onboarding & Audit (One-Time)

Includes the full technical audit, backlink audit, competitor research, keyword mapping and tracking set-up. Fee: $249. This fee is waived for clients who commit to 3 months or more.

## Prepayment Discount

Pay for 3 months in advance and get 7% off the package price.

## Additional Costs (Only If You Choose Them)

There are no hidden costs. The monthly package covers all the work and the SEO tools. The items below are optional and always quoted and approved by you before any money is spent:

- Paid guest posts: placements on high-authority travel, food and wellness sites. Priced per placement according to the site’s authority (typically $50–$500+ per post). Charged at cost.

- Paid PR: press-release distribution or sponsored features in travel and lifestyle media, priced per campaign.

- Website development: design or development work beyond SEO fixes (e.g. a redesign or a new booking engine), quoted separately.

- Photography / video: new professional photos or video for the website and Google profiles.

- Paid advertising budget: Google Ads or Meta Ads spend, if added later.

# 8. Terms & Conditions

## 8.1 Payment Terms

- 35% upfront: paid at the start of each monthly cycle, before work begins. The first payment confirms the project start date.

- 65% balance: paid at the end of each monthly cycle, calculated from the project start date (for example, a project that starts on the 5th has its cycle end on the 4th of the following month).

- Invoices are payable within 5 days. Work may be paused if a payment is more than 7 days late, and resumes once it is paid.

- All prices are in USD. Bank, transfer and currency-conversion fees, and any applicable taxes, are paid by the client.

## 8.2 Engagement Term

- Initial commitment of 3 months, matching the 90-day plan. After that, the engagement continues month to month.

- Either party may end the engagement with 15 days’ written notice before the next cycle begins. Work completed up to that date is billed in full.

- You may move to a different package at the start of any new monthly cycle.

## 8.3 Approvals & Content

- Nothing is published on the website, Google Business Profiles or any third-party platform without your review and approval.

- Please send approval or feedback within 3 business days. If approvals are delayed, the affected deliverables move into the next cycle and are not lost.

- Each deliverable includes up to 2 rounds of revisions.

- Once the related payment is complete, all content created for you belongs to Gandum Uluwatu.

## 8.4 Access & Responsibilities

- The client provides access to the website (CMS), GA4, Google Search Console and all three Google Business Profiles within the first week.

- The client provides accurate business information, photos, menus, treatment details and offers.

- Delays in getting access or information may push timelines back.

## 8.5 Results & Reporting

- SEO and AI visibility depend on third-party platforms (Google, OpenAI, Perplexity and others) that we do not control. No specific ranking, traffic or AI-citation result can be guaranteed. We do guarantee the agreed deliverables, honest work and full transparency.

- We use white-hat, search-guideline-friendly methods only.

- A monthly report is shared within 5 business days after each cycle ends. All working sheets stay accessible to you at all times.

## 8.6 Confidentiality

- All business data, logins and performance information are kept strictly confidential and used only for this project. Access is returned or removed when the engagement ends.

# 9. Next Steps

- Choose a package (we recommend Horizon).

- Confirm the start date and pay the 35% upfront for the first cycle.

- Share access to the website, GA4, Search Console and all 3 Google Business Profiles.

- Kick-off call. Onboarding and the audit begin the same week.

We look forward to working with you Thank you for considering this proposal. Please reach out with any questions. We are happy to adjust the scope to fit your goals and budget. [Your Name] · [Email] · [Phone / WhatsApp] · [Website / LinkedIn]

| Acceptance |  |
| --- | --- |
| Selected package |  |
| Project start date |  |
| Client name & signature |  |
| Date |  |